## NCP Validation Status
# | Suite / Check | Description | Status | Result / Metrics | Adaptation Details | Adaptation Type
Suite 1 — Control Plane
1.1 | API Health / Auth checks | AccessKeyCreatedCheck, TenantCreatedCheck, AccessKeyAuthenticatedCheck, TenantListedCheck, TenantInfoCheck, StepSuccessCheck | PASSED | STS / EC2 / IAM endpoints all reachable.
1.2 | AccessKeyDisabledCheck | Verify iam:UpdateAccessKey can disable an access key | BLOCKED | iam:UpdateAccessKey returns 'Not Implemented' on zCompute. Jira: NK-19406 | Platform gap — requires engineering work in zCompute core. | Platform Gap
1.3 | AccessKeyRejectedCheck | Verify disabled key is rejected on subsequent API calls | EXCLUDED | Depends on 1.2 — excluded until platform implements key disable.
Suite 2 — IAM
2.1 | All IAM checks (5 checks) | User / group / role CRUD, policy attachment, assume-role | PASSED | All 5 checks passing.
Suite 3 — VM (GPU Virtual Machines)
3.1 | Full VM lifecycle | Create / stop / start / reboot / delete | PASSED | Instance: zh1.52xlarge ¦ 208 vCPUs ¦ 8x H100 SXM5 80GB ¦ Ubuntu 24.04
3.2 | GpuCheck (initial / post-start / post-reboot) | nvidia-smi on each lifecycle phase | PASSED | 8x H100 ¦ Driver 535.309.01 verified across all phases.
3.3 | VcpuPinningCheck / PciBusCheck / HostSoftwareCheck / ContainerRuntimeCheck | Host-level GPU and software checks | PASSED | Docker: OK ¦ NGC login: OK
3.4 | SerialConsoleCheck / ConsoleRbacCheck | Serial console access via GetConsoleOutput | EXCLUDED | GetConsoleOutput returns HTTP 500 — not implemented in zCompute. | Platform gap — serial console API not supported. | Platform Gap
3.5 | NimHealthCheck / NimModelCheck / NimInferenceCheck | NIM container inference on GPU VM | IN PROGRESS | Fix deployed (GPU passthrough for Docker). Re-run pending. | NIM Docker container required --gpus=all flag not passed by default in VM suite manifest. Fixed in suite config. | Config Change
Suite 4 — Network
4.1 | VpcCrudCheck / SubnetConfigCheck / VpcIsolationCheck | VPC and subnet lifecycle and isolation | PASSED | Single AZ (symphony). CIDR isolation verified.
4.2 | SgCrudCheck / SecurityBlockingCheck / VpcIpConfigCheck | Security group rules and IP configuration | PASSED
4.3 | DhcpIpManagementCheck / StablePrivateIpCheck / FloatingIpCheck / VpcPeeringCheck | IP management and Elastic IP | PASSED | EIP switch: ~1.6s (limit 10s). Private IP stable across stop/start.
4.4 | NetworkConnectivityCheck / TrafficFlowCheck | End-to-end connectivity via SSM | EXCLUDED | Requires AWS SSM agent. Discussing alternative implementation with NVIDIA. | zCompute has no SSM. Pending NVIDIA approval for custom probe alternative. | Platform Gap / Pending
4.5 | LocalizedDnsCheck | Route 53 private hosted zone | IN PROGRESS | Route 53 partially supported on zCompute. Under investigation.
4.6 | SgWorkloadScopingCheck / SgSubnetScopingCheck / SgServiceScopingCheck | Network ACL scoping checks | EXCLUDED | NACLs (CreateNetworkAcl) return AuthFailure — not supported on zCompute. | zCompute uses SG-only security model. No NACL API available. | Platform Gap
4.7 | ByoipCheck | Bring-your-own IP | EXCLUDED | PDM to confirm irrelevance to Zadara.
4.8 | BackendSwitchFabricCheck / NvlinkDomainCheck | Backend switch fabric and NVLink domain | IN PROGRESS | Pending run.
Suite 5 — Kubernetes (EKS-D on zCompute)
5.1 | K8sNodeCountCheck / K8sExpectedNodesCheck / K8sNodeReadyCheck | Node count and readiness | PASSED | 6 nodes Ready: 3 control-planes + 1 CPU worker + 2 GPU workers
5.2 | K8sNvidiaSmiCheck / K8sDriverVersionCheck / K8sGpuPodAccessCheck | GPU driver and pod access verification | PASSED | Driver 575.57.08 on both GPU nodes. nvidia-smi OK.
5.3 | K8sGpuCapacityCheck / K8sGpuOperatorNamespaceCheck / K8sGpuOperatorPodsCheck / K8sGpuLabelsCheck / K8sMigConfigCheck | GPU operator and capacity checks | PASSED | 16x nvidia.com/gpu allocatable ¦ GPU Operator in zadara-system (35 pods) ¦ MIG disabled
5.4 | K8sPodHealthCheck / K8sNoPendingPodsCheck | Pod health across all namespaces | PASSED | All pods Running or Succeeded. No pending pods.
5.5 | K8sDualStackNodeCheck | IPv4/IPv6 dual-stack verification | EXCLUDED | Cluster is single-stack IPv4 only — auto-skipped by suite. | zCompute cluster is IPv4 only. Suite auto-skips; no manual action required. | N/A
5.6 | K8sNetworkPolicyCheck | NetworkPolicy enforcement (allow / ingress-deny / egress-deny) | PASSED | Cilium CNI. All 3 subtests pass (IPv4).
5.7 | K8sCsiStorageTypesCheck / K8sCsiStorageQuotaApiCheck / K8sCsiTenantScopedCredentialsCheck / K8sCsiProvisioningModesCheck | EBS CSI storage checks | PASSED | Block storage via ebs-sc. Dynamic provisioning verified. Shared-FS/NFS skipped (not on zCompute). | EBS CSI deployed by zadara-vm-chart lacked credentials and endpoint: - Created aws-ebs-csi-credentials secret in zadara-system - Set AWS_EC2_ENDPOINT to zCompute EC2 API URL (https) - Mounted zCompute CA cert and set SSL_CERT_FILE - Added hostAliases for TLS IP SAN mismatch workaround (IP -> hostname) | Config Change (kubectl patch)
5.8 | K8sOidcIssuerCheck | OIDC discovery endpoint verification | PASSED | Issuer: https://kubernetes.default.svc.cluster.local
5.9 | K8sNimInferenceWorkload | NIM inference on H100 SXM5 in Kubernetes | PASSED | NIM inference validated on H100 SXM5.
5.10 | K8sNimHelmWorkload-1b | llama-3.2-1b-instruct via Helm chart | PASSED | Throughput: 12.98 req/sec ¦ 1,854 tokens/sec
5.11 | K8sNimHelmWorkload-3b | llama-3.2-3b-instruct via Helm chart (single GPU) | PASSED | Throughput: 20.77 req/sec ¦ 2,851 tokens/sec Note: multi-GPU tensor parallelism disabled — IMEX/NVLink init fails on zCompute VMs.
5.12 | K8sApiServerMetricsCheck / K8sControlPlaneLogsCheck | Prometheus metrics and control plane log retrieval | PASSED | 391 Prometheus metrics. Logs from kube-apiserver, kube-scheduler, kube-controller-manager.
5.13 | K8sNcclWorkload (single-node allreduce) | NCCL allreduce across all 8 GPUs on a single node | PASSED | Average bus bandwidth: 110 GB/s ¦ Out of bounds: 0 | Previous cluster had a duplicate IP on rocep75s0 NIC — excluded it via NCCL_IB_HCA. New cluster: all 8 RoCE NICs confirmed unique IPs. NIC exclusion removed. | Code Change (manifest env var)
5.14 | K8sNcclMultiNodeWorkload | NCCL allreduce across 2 nodes x 8 GPUs = 16 GPUs total | PASSED | Max bus bandwidth: 461 GB/s ¦ Avg: 116 GB/s ¦ Threshold: 350 GB/s ¦ Out of bounds: 0 | Multiple adaptations required: 1. NCCL_NET_GDR_LEVEL: '0' (disabled) -> 'SYS' (GPUDirect RDMA enabled) 2. NCCL_IB_HCA: removed 4-NIC exclusion — all 8 NICs now active 3. NCCL_NVLS_ENABLE=1 added — NVLink Switch tree enabled 4. min_bus_bw_gbps threshold raised: 30 -> 350 GB/s Result: 461 GB/s (was 115 GB/s before fixes) | Code Change (manifest) + Config Change (threshold)
5.15 | K8sGpuStressWorkload | GPU stress test on all GPU nodes | PASSED | Passed on both gpu-worker-0 and gpu-worker-1. | pytorch:25.04-py3 image (~20 GB) was not pre-pulled — pods timed out on first attempt. Added pytorch image pre-pull DaemonSet to post_cluster_setup.sh. | Config Change (post_cluster_setup.sh)
5.16 | K8sCncfConformanceCheck | CNCF certified-conformance mode (v1.35.2) | PASSED | 446 / 446 [Conformance] tests passed ¦ 0 failed ¦ 6,914 skipped (cloud-specific / feature tests not required for conformance) Run time: ~2h 20min | 1. kube-apiserver --service-node-port-range was 20000-32767 (non-standard). CNCF conformance validates ports in standard range 30000-32767. Fixed: sed on static pod manifest on all 3 control-plane nodes. 2. k8s_conformance.py improved: failure messages and JUnit XML now included in output for debugging. | Cluster Fix (kube-apiserver manifest) + Code Change (k8s_conformance.py)
5.17 | K8sApiNetworkAclCheck | Verify K8s API endpoint is blocked from unauthorized network | IN PROGRESS | External VM identified. SG configuration in progress to block port 6443 from external machine. | Test requires 'unauthorized_probe' command in config (SSH to external VM -> curl API -> expect timeout). This is not a NACL requirement — SG-level block is sufficient to pass. | Config Change (k8s.yaml)
5.18 | K8sNodePoolCheck | Managed node pool lifecycle (create / scale / delete) | EXCLUDED | Static cluster — zCompute has no managed node pool API. | zCompute does not expose a node pool management API. Test permanently excluded. | Platform Gap
Suite 6 — Security
6.1 | All security checks | Encryption at rest/transit, secrets management, RBAC, audit logs | NOT STARTED | Not started.
Suite 7 — Image Registry
7.1 | All image registry checks | Private registry push/pull, ECR-compatible API | NOT STARTED | Not started. No S3 endpoint on zCompute — potential platform gap. | zCompute lacks S3-compatible object storage endpoint required by image registry suite. | Platform Gap (under investigation)
Suite 8 — Bare Metal
8.1 | All bare metal checks | Direct hardware provisioning, BMC, IPMI | NOT STARTED | Not started. May not apply — zCompute delivers GPU via VMs, not bare metal.

## Adaptations Summary
Check | Name | Type | What Changed | File / Location
5.7 | EBS CSI credentials & endpoint | Config Change | zadara-vm-chart deployed EBS CSI without AWS credentials or zCompute endpoint. - Created aws-ebs-csi-credentials secret in zadara-system - Set AWS_EC2_ENDPOINT to zCompute EC2 API (https) - Mounted zCompute CA cert; set SSL_CERT_FILE env var - Added hostAliases: IP -> hostname to resolve TLS IP SAN mismatch | kubectl patch deployment/ebs-csi-controller -n zadara-system
5.13 | NCCL single-node — NIC exclusion removed | Code Change | Previous cluster: duplicate IP on rocep75s0 NIC required exclusion (NCCL_IB_HCA=^rocep75s0). New cluster: all 8 RoCE NICs confirmed unique IPs. NIC exclusion removed from both NCCL manifests. | nccl_allreduce_job.yaml nccl_allreduce_mpijob.yaml
5.14 | NCCL multi-node — GPUDirect RDMA + NVLink Switch | Code Change + Config Change | 1. NCCL_NET_GDR_LEVEL: '0' -> 'SYS' (GPUDirect RDMA enabled) 2. NCCL_IB_HCA: removed 4-NIC exclusion — all 8 RoCE NICs active 3. NCCL_NVLS_ENABLE=1 added (NVLink Switch tree) 4. min_bus_bw_gbps: 30 -> 350 GB/s Impact: max bandwidth 115 GB/s -> 461 GB/s | nccl_allreduce_mpijob.yaml isvctl/configs/providers/zcompute/ config/k8s.yaml
5.15 | GPU stress test — pytorch image pre-pull | Config Change | pytorch:25.04-py3 image (~20 GB) not pre-pulled. GPU stress pods timed out on first run. Added pytorch pre-pull DaemonSet to post_cluster_setup.sh. | scripts/k8s/post_cluster_setup.sh
5.16 | kube-apiserver service-node-port-range | Cluster Fix | zadara-vm-chart set --service-node-port-range=20000-32767 (non-standard). CNCF conformance tests require ports in 30000-32767. Fixed via sed on static pod manifest on all 3 control-plane nodes. | /etc/kubernetes/manifests/ kube-apiserver.yaml (all 3 control-plane nodes)
5.16 | CNCF conformance output improvements | Code Change | k8s_conformance.py did not include failure messages in output — only test names. Added: case.message in set_failed output (trimmed to 800 chars). Added: JUnit XML saved to /tmp/conformance-junit.xml for post-mortem analysis. | isvtest/src/isvtest/validations/ k8s_conformance.py
CCM | AWS Cloud Controller Manager — TLS fix | Config Change | CCM failed: x509 certificate for 172.29.0.20 has no IP SANs (only *.zadara-qa.com DNS SANs). - Added hostAliases to CCM DaemonSet: zcompute-api.zadara-qa.com -> 172.29.0.20 - Updated cloud.conf: http:// -> https:// with hostname - Fixed region: us-east-1 -> symphony - Fixed gcfg key casing: KubernetesClusterID -> kubernetesclusterid | kubectl patch daemonset aws-cloud-controller-manager -n kube-system kubectl patch configmap zadara-cloud-config -n kube-system
Infra | post_cluster_setup.sh — skip conditions | Code Change | Script assumed a fresh cluster. Failed when zadara-vm-chart already deployed CCM, EBS CSI, GPU Operator. Fixed: skip conditions now check for existing deployments/daemonsets, not only Helm releases. Also fixed: GPU Operator namespace check (nvidia-gpu-operator -> zadara-system), replaced Calico check with Cilium, updated default HGX node IPs. | scripts/k8s/ post_cluster_setup.sh
Infra | Cilium operator — scaled to 1 replica | Config Change | zadara-vm-chart deploys Cilium operator with 2 replicas causing leader election issues. Scaled to 1 replica. | kubectl scale deployment cilium-operator -n kube-system --replicas=1